## Sheet1
Risk ID | Risk Title | Risk Description | Affected Asset/System | Threat | Vulnerability / Control Weakness | Existing Controls | Inherent Likelihood | Inherent Impact | Inherent Risk Score | Inherent Risk Level | Treatment | Treatment Action | Risk Owner | Target Date | Status | Projected Residual Likelihood | Projected Residual Impact | Projected Residual Risk Score | Projected Residual Risk Level | Validation / Evidence | Review Date
R-001 | Unauthorized Administrative Access Due to Missing MFA | Compromised employee credentials could allow an unauthorized individual to access the Patient Portal administrative environment, potentially exposing PHI/PII and creating regulatory, operational, and reputational impact. | Patient Portal Administration System | Compromised credentials resulting in unauthorized access | MFA is not required for administrative access | Username/password authentication, role-based access controls (RBAC), and authentication logging | 4 | 5 | 20 | Critical | Mitigate | Implement MFA for administrative access and verify appropriate access controls | IAM Manager | 2026-10-30 | In Progress | 2 | 5 | 10 | High | Review MFA configuration and enrollment records and perform authentication testing to verify that administrative users cannot access the Patient Portal administration system using only a username and password | 2026-11-06